QuietReady.ai

3–4 Week Launch Plan

From working prototype to first paying customer

Prepared: March 8, 2026

## What's Already Built

| ✅ Frontend Onboarding Flow · 9-step questionnaire (React/JSX) · Household, pets, dietary, food philosophy · Storage space + container fit check · Coverage & budget dual-slider with live math · Utilities, equipment, container selection · Plan review + recipe PDF preview · Success / next-steps screen | ✅ Backend Infrastructure · Supabase schema — all 10 tables, RLS, triggers · Node.js / Express API — 14 endpoints · Supabase Auth integration · Stripe subscription + webhook handling · Auto-generated order numbers · Shipment confirmation → portal trigger · PDF generation (ReportLab) · EC2 + Nginx + PM2 deploy scripts |
| --- | --- |
| ✅ Food Planning Engine · 4 food philosophies with full product lists · Real bulk pricing per philosophy · Pet food costs by type and size · Container volume + space fit validation · Storage overflow warning with fix suggestion · Estimated supply cost + months-to-goal | ✅ PDF Recipe Guide · Cover page with customer stats · Storage inventory table with container IDs · Recipes tied to delivered inventory · Pet food section with orange labeling · Rotation & replenishment schedule · Auto-regenerates on shipment confirmation |

## Launch Scope — What We're NOT Building Yet

The following are explicitly deferred post-launch. Every item below that ships on day one adds risk to the timeline.

| 🚫 Deferred to Post-Launch · Automated purchasing (Amazon PA API) · Freshbooks billing integration · Automated email sequences / drip · Rotation reminder notifications · Storage map / container diagram generator · Mobile app · Multi-location storage mapping · Inventory scanning / barcode | ✅ Manual Process at Launch (That's OK) · Purchasing: Admin places orders manually on Amazon/suppliers · Billing: Admin creates invoices in Freshbooks manually · Onboarding: Admin reviews each new signup · Shipment tracking: Admin marks items confirmed in dashboard · PDF: Generated on-demand from admin dashboard · Email: Plain transactional emails only |
| --- | --- |

## The 4-Week Sprint

| WEEK 1 | Days 1–7 · Infrastructure & Auth |
| --- | --- |
| You | Provision EC2 + Supabase Launch t3.small, assign Elastic IP, run setup_ec2.sh, create Supabase project | READY |
| You | Run database schema Paste 001_schema.sql into Supabase SQL Editor → run. Verify all 10 tables created. | READY |
| You | Configure Stripe Create $30/mo membership Price, set up webhook endpoint, copy all keys to /etc/environment | READY |
| Claude | Customer auth flow Supabase magic-link login, auth callback page, session management in React frontend | BUILD |
| Claude | Wire onboarding → API Connect Submit button to POST /api/onboarding/submit. Handle success/error states. | BUILD |
| Claude | Deploy frontend to EC2 Vite build config, deploy dist/ to Nginx, verify HTTPS on quietready.ai | BUILD |
| You | End-to-end test Sign up as test customer. Verify: DB rows, Stripe customer, welcome email, login link. | TEST |

| WEEK 2 | Days 8–14 · Customer Portal |
| --- | --- |
| Claude | Portal dashboard Inventory overview, active order status, pending placement instructions, PDF download button | BUILD |
| Claude | Placement instructions UI Card per unacknowledged instruction: container code, label text, 'Mark Done' button | BUILD |
| Claude | Order history screen Timeline of orders, per-item status (ordered / shipped / confirmed) | BUILD |
| Claude | Rotation schedule view Table: item → expiry date → replenish-by date → status badge | BUILD |
| Claude | Account settings page Update name, phone, dietary notes. Pause / cancel subscription flow. | BUILD |
| You | Portal review Sign in as test customer. Walk every screen. Note UX issues. | TEST |

| WEEK 3 | Days 15–21 · Admin Dashboard |
| --- | --- |
| Claude | Admin login + guard Separate admin login, redirects non-admins, role-based nav | BUILD |
| Claude | Customer list view Table: name, email, status, coverage goal, monthly budget, last order, quick actions | BUILD |
| Claude | Customer detail view Full profile: household, prefs, containers, inventory, order history, all in one screen | BUILD |
| Claude | Confirm shipment flow Per order-item: 'Mark Received' button → fires DB trigger → updates portal instantly | BUILD |
| Claude | Create order screen Admin manually creates monthly order for a customer, adds line items, sets supplier | BUILD |
| Claude | PDF regenerate button Admin can force-regenerate a customer's Recipe Guide PDF from their detail page | BUILD |
| You | Admin walkthrough Process a test order end-to-end: create order → add items → confirm shipment → verify portal updates | TEST |

| WEEK 4 | Days 22–28 · Polish, Test & Launch |
| --- | --- |
| Both | Fix Week 1–3 bugs Work through the issue list from testing. No new features. | BUILD |
| Claude | Error handling pass Every API call has a loading state, error message, and retry. No blank screens. | BUILD |
| Claude | Mobile responsive pass Portal and onboarding work on iPhone. Admin dashboard desktop-only is acceptable. | BUILD |
| You | Real data test Sign up as yourself. Go through full onboarding. Place a real small order manually. | TEST |
| You | Stripe live mode Switch from test keys to live keys. Process $1 test charge. | READY |
| You | Invite beta customers 3–5 people you trust. Offer first month free. Get real feedback. | READY |
| Both | Launch day quietready.ai goes live. Monitor logs. Be available. | READY |

## Critical Path — What Can Block Launch

These are the items that, if delayed, push the launch date. Everything else can slip without consequence.

| Task | Why It Blocks Launch | Owner / Deadline |
| --- | --- | --- |
| EC2 + Supabase provisioned | Nothing can be deployed or tested without live infrastructure | You → Day 1–2 |
| Stripe price ID + webhook configured | Onboarding submit fails without a valid Stripe price to attach subscription to | You → Day 2–3 |
| Onboarding → API wired | Everything downstream (portal, admin, PDF) depends on customer records being created | Claude → Day 5–6 |
| Admin 'Confirm Shipment' working | This is the core operational workflow — without it you can't service customers at all | Claude → Day 17–18 |
| Stripe live mode tested | Can't charge real customers without switching to live keys and verifying a real charge | You → Day 25–26 |

## Risk Register

| Risk | Impact | Mitigation | Level |
| --- | --- | --- | --- |
| Infrastructure setup takes longer than expected | Delays all development by days | Provision EC2 + Supabase on Day 1 before writing any code | HIGH |
| Stripe webhook integration issues | Subscriptions don't activate, customers can't be billed | Test with Stripe CLI locally before deploying. Use test mode throughout dev. | HIGH |
| 4-week timeline too tight | Soft launch with bugs or incomplete features | Scope is already cut to minimum. Admin dashboard manual ops cover any gaps. | MED |
| Amazon supplier API unavailable at launch | Can't automate purchasing | Already planned as manual — admin places orders directly. No blocker. | LOW |
| First beta customers find critical UX bugs | Bad first impression | Invite trusted contacts only for beta. Offer month 1 free in exchange for feedback. | MED |
| PDF generation fails on EC2 | Customers can't download recipe guide | PDF is a nice-to-have at launch. Portal works without it. Fix post-launch. | LOW |

## Your Day 1 Checklist (Do These Before Anything Else)

| 1 | Create Supabase project at supabase.com — copy URL + anon key + service_role key | supabase.com |
| --- | --- | --- |
| 2 | Launch EC2 t3.small (Ubuntu 24.04), assign Elastic IP, open ports 22/80/443 | AWS Console |
| 3 | Run sql/001_schema.sql in Supabase SQL Editor — verify 10 tables appear | Supabase Dashboard |
| 4 | Create Stripe account, create $30/mo recurring price, copy price_xxx ID | stripe.com |
| 5 | Set up Stripe webhook → quietready.ai/api/webhooks/stripe, copy signing secret | Stripe Dashboard |
| 6 | SSH into EC2, run deploy/setup_ec2.sh, fill in /etc/environment with all keys | EC2 terminal |
| 7 | Point quietready.ai DNS A record → EC2 Elastic IP | Your DNS provider |
| 8 | Run: certbot --nginx -d quietready.ai -d www.quietready.ai | EC2 terminal |
| 9 | Deploy API: npm install + pm2 start ecosystem.config.cjs | EC2 terminal |
| 10 | Verify: curl https://quietready.ai/api/health returns {"status":"ok"} | Terminal |

## Infrastructure Cost at Launch

| Service | Plan | Cost/mo | Notes |
| --- | --- | --- | --- |
| Amazon EC2 | t3.small | $17 | Upgrade to t3.medium at ~50 customers |
| Supabase | Free tier | $0 | Up to 500MB DB, 1GB storage, 50k auth users |
| Stripe | Pay-as-you-go | 2.9% + $0.30 | Per transaction only — no monthly fee |
| Domain (quietready.ai) | Annual | ~$3/mo | Already registered |
| SSL (Let's Encrypt) | Free | $0 | Auto-renews via certbot |
| Freshbooks | Lite plan | $17 | Up to 5 clients. Upgrade as you grow. |
| Total at launch |  | ~$37/mo fixed | + 2.9% on each Stripe transaction |

Break-even: 2 customers covers all fixed monthly costs. Everything beyond that is margin.